## Issues_Actions Log
Public Accountability Meeting: Action Log last updated:03.07.18
No. | Area | Issue/Action | Date Raised | Assigned To | Target Date | Update & Resolution | Status | Date Closed
221 | Safeguarding | BD&I meeting, outlining how the CJ partnership can work better together and with Community Safety Partnerships to improve processes and performance and provide a coherent offender management system. | 23.01.18 | Allan Harder/Jenni Newberry | 26.06.18 | 17.07.18 Update: The option paper was presented to the BD&I board by Allan Harder, and during this it was supported by both the NPS and CRC who have been fully engaged and support the new process. Details of the changes were then taken to the LCJB by Jenni, and a further meeting on 20th August is planned with Allan Harder, ACC Cain, Jenni Newberry and PCC. 26.06.18 Update: Options were presented to the BD&I board this month. 22.05.18 Updates: a review has taken place and options are being presented at the BD&I meeting. An update to be presented at the next meeting. 02.02.2018 Update: JN emailed leads for IOM within NYP, CRC & NPS on 01/02/18 to confirm the request for an IOM ‘Options Paper’ to come to the BD&I Board. JN has asked leads to come back if there are any concerns or a need to meet to discuss. JN will table agenda item at 28/02/18 BD&I Board to discuss the content of proposed paper and will agree a deadline with partners aligned to following BD&I Board scheduled for May/June 18. IOM ‘Options Paper’ will then be tabled for following LCJB. | Open
224 | Kirby Misperton | lessons learned' on the Operation - On completion this is to be presented back to PAM | 24.04.18 | ACC Oliver | 26.06.18 | 06.07.18 Update: An update will be brought back to the meeting once the ongoing court cases have reached their conculsion. 26.06.18 Update: Although the operation has come to a conclusion there are still court cases on-going, therefore the conclusions will be brought back once that activity has concluded. There have been meetings with stakeholders that have been productive and feedback from those meeting are been worked on. | Open
228 | Safeguarding | How is a breech of a harassment order recorded? And if there are several breeches does this trigger a review which then changes the status from Harassment to Stalking? | 22.05.18 | Allan Harder | 26.06.18 | 17.07.18 Update: The response to breeches of orders varies which is not unique to North Yorkshire. Some are dealt with as a breach in isolation, and others are investigated as a further offence and a breach. The further offence will require a charge decsion and on occassions this will result in a charge for both. The amened policy promotes a proactive investigation for the additional offence inconjunction with the breach which is intended to provide a more conistent approach. | Closed | 24.07.18
229 | Safeguarding | Provide numbers of PINS & HINS issued for the last 5 financial years | 22.05.18 | Allan Harder | 26.06.18 | 17.07.18 Update: Details received by the OPCC | Closed | 24.07.18
230 | Safeguarding | Provide a list of names and contact details of those who attended the National Stalking & Harassment conference | 22.05.18 | Allan Harder | 26.06.18 | 17.07.18 Update: Sam Hames attended the national stalking and harassment confernece in London, and two of the workshops. Sam has also attended the North Yorkshire police Stalking and Harassment workshop and shared the learning from this event which was very informative. | Closed | 24.07.18
231 | Safeguarding | Breakdown of how many of the incidents are section 2 and section 4 offences | 22.05.18 | Allan Harder | 26.06.18 | 17.07.18 Update: Details received by the OPCC | Closed | 24.07.18
232 | Safeguarding | Review of force policy on stalking & harassment being carried out, results of that to be feedback to meeting | 22.05.18 | Allan Harder | 24.07.18 | 17.07.18 Update: Policy has been reviewed and this includes the use of PINs / HINs. The national direction is that the use of these will cease and this appraoch will be followed by North Yorkshire Police. The North Yorkshire Police workshop was beneficial and some of the points discussed will also feed into to the new policy that will go live in July | Closed | 24.07.18
233 | Performance Pack | Trend type to be added to the S136 slide | 26.06.18 | ACC Cain | 27.07.18 | 17.07.18 Update: the pack has been updated to reflect this. | Closed | 24.07.18

## Closed Issues_Actions (hidden)
No | Area | Issue/Action | Date Raised | Assigned To | Target Date | Update & Resolution | Status | Date Closed
123 | OPCC | TT to provide a progress update to JM in relation to the Case Management Software. | 01.03.16 | Thomas Thorp |  | UPDATE 28.02.17 – JN to provide an update on this meeting UPDATE 28.03.17 – JM has asked Richard Jones (Head of ICT) to review Case management software with as a case study. Procurement process ongoing. | Clsd | 27.06.17
154 | Commissioning | JN to work on getting an item on the agenda at the Health and Wellbeing Board as they have overarching scrutiny responsibility in drug treatment and alcohol treatment services. | 01.02.16 | Jenni Newberry |  | UPDATE 28.02.17 – LWi to review the Health & Wellbeing minutes & papers from 8th March 2017, will update the Board. UPDATE 28.03.17 – Bill Scott attended Health & Wellbeing Board on behalf of LW, LW awaiting minutes from the last meeting. WN to talk to BS about Mental Health Conference UPDATE 25.04.17 – BS currently attempting to organise a date for the Mental Health Conference. With the general election imminent, this may not occur. WN to discuss further with BS. | Clsd | 27.06.17
156 | OPCC | Timetable to be created which details the roll-out of the scheme | 01.02.16 | Will Naylor |  | UPDATE 28.02.17 – DJ advised it would be appropriate to incorporate this into a wider road safety review later in the year which will involve all safety camera vans, where community speed watch will have been running for a while, may also include Newcastle University Report (NUR). To be scheduled in due course. UPDATE 28.03.17 – JM visited Athena house and viewed new safety vans. DJ advised of planned publicity/ press release Outcome of the work undertaken by Newcastle University will be fed into the Academic Board. UPDATE 25.04.17 – LW to send the information from the NUR to the Academic Board, then to NYP/ OPCC with an explanation on content. The full report has not been received yet. WN will bring road safety to this board, will wait for the report details and collate the information. | Clsd | 27.06.17
167 | Performance Pack | To look at the inclusion of outcome-based performance within the performance pack to assist in providing a context in some areas. | 23.08.16 | Lisa Winward |  | UPDATE 28.02.17 – WN and LWi advised Stephen Murray (Performance Manager) is gathering information in relation to Satisfaction surveys. Ideas on developing futures areas of business and collaborate all information into one place that will ‘feed’ into the Performance Pack. LW and ME discussed the future of Governance and Performance meeting would ‘feed’ into this process, focusing on organisational performance opposed to operational performance in operational meetings, giving a view to the health of the whole organisation and reporting to this meeting and filtering through. UPDATE 28.03.17 – WN/LWi/SM are developing the performance approach to reflect the new Police & Crime Plan. WN to meet with SM to discuss. Findings to be shared outside this meeting. JM highlighted other methodologies for obtaining feedback from qualitative work, alongside surveys, should be used. UPDATE 25.04.17 – Meeting on 09.05.17 to discuss the approach to the business plan from the Police & Crime Plan. WN & TT confirmed that they have discussed that the performance team have carried out an analysis of what has been collected and recorded from the public. From that consideration to possibilities to gain further information from the public has been deliberated, TT & WN to meet and discussed further. | Clsd | 25.07.17
177 | Community Messanger | Look at potential advertising campaign opportunities in relation to community messaging. | 26.10.16 | Richard Anderson |  | UPDATE 28.02.17 – WN and Louise Wood are working to invite companies to tender and obtain professional support to advertise the community messaging out to the community as best as possible. Had been delayed due to hitting ‘teething problems’ however now can be revisited. Simon Jones is reviewing feedback received through community messaging, interaction with OPCC/ NYP. A full and true update on this is required. UPDATE 28.03.17 – WN liaising with LW about the potential marketing of Community Messaging, (this was initially linked with the Community Mapping exercise (report to be circulated) . LWi advised of an engagement event next month, the Partnership Hub are attending to share experiences of Community Messaging. 11.04.17 update – report; ‘Using Mosaic to inform Community Engagement’ circulated. UPDATE 25.04.17 – Partnership hub to provide a collective briefing as to what the next steps are outlining what is happening with the data that has been collected. JM also noted that it would be beneficial for the next meeting to have information on how are those partnerships contributing to creating a more strategic approach to demand reduction and prevention across the force area rather than isolated geographical locations, lessons learnt from them and how future pilots/ initiatives are developed from this. Report has been issued and will be re-circulated | Clsd | 25.07.17
179 | OPCC | Meeting to be arranged for Mark Bates to discuss demand modelling with the PCC and Deputy PCC | 24.01.17 | Will Naylor |  | UPDATE 28.02.17 – PC advised he is putting together a working group with Steve Thomas to look at the demand for an investigation of serious crime teams and further modelling. PC to advise further on Mark Bates return. | Clsd | 27.06.17
182-187 | Performance Pack | Headings shown on the pie chart on slide 9 (Monthly Incident Volume) are to be split into urban and rural and figures to be shown as such A review on the retention of call handlers/ dispatcher staff to be carried out A review is to be carried out in reference to the options given on the 101 automated service, including the order in which the options are given and which options are mostly abandoned. OPCC to summarise a ‘user-friendly’ version of the 101 presentations for the website. The board to be updated on progress against the Buzzz review | 28.02.17 | Lisa Winward |  | Informaiton received and work in progress | Clsd | 27.06.17
190-195 | FCR Peer Review | The board would like to have sight of the Force Control Room Peer review from Police Service – Northern Ireland to gain an understanding of how the key findings will contribute to the Improvement/Action Plan. Details of dip samples from internal & external recruits and internal customers who have asked HR to facilitate their recruitment needs. Initially, start with Head of Functions who has recruited during the last 12 month period for initial feedback to include areas of difficulties and positives. May need to consider utilising external agencies to carry out this work to alleviate capacity issues and possible bias. Review of how HR scrutinises the effectiveness of services delivered by external agency worker suppliers (active contract management/supplier management) also explore other opportunities for short notice recruitment. Risk management procedure to be revisited to allow a smoother transition for work placement for school/college students. LWi to review. Future versions of resource capability to include police staff as well as police officers and for FS to be included in this work. Research to be carried out on costings and opportunities for qualifications for Officers and Police Staff including apprenticeships. JM requested further information on the Apprenticeship scheme for both officers and staff – to be progressed via EG. | 28.03.17 | Lisa Winward |  | Picked up by External Audit, draft report will be available in 10 working days. | Clsd | 25.07.17
196-198 | Operational Updates | Feedback is required on Op Tanus in regard to collaboration opportunities and ‘feeling safe’. Rural Task Force (RTF) popularity/ knowledge needs to be highlighted. PC to consider effective channels to raise awareness of the RTF with LW with the suggestions of Rangers/ National Parks, working with NFU etc. JP to supply an HR spreadsheet with total figures for the workforce, which will be added to next month’s meeting. | 28.03.17 | Lisa Winward |  | Informaiton received and work in progress | Clsd | 27.06.17
199-201 | OPCC | In relation to savings made due to collaborative procurement, JM requested to see these figures. JP to provide estimates as discussed. It was agreed that the thematic collaboration report can be extended to look deeper into each individual collaboration to gain a greater perspective of need, which may be a possible starting point of benefits for future collaborations with view to resources/ parameters required, gaining an understanding of what the benefits are for the public of North Yorkshire. AO/ WN to initiate further. Further to the discussions after the thematic collaboration report was presented it was suggested to organise a meeting between the 7 PCCs to discuss what specialities each force can offer to collaboration. JM/ WN to discuss with Simon Dennis (CEO Cleveland OPCC). | 25.04.17 | Will Naylor |  | Informaiton received and work in progress | Clsd | 27.06.17
202-206 | IOM | RA to send OPCC information on Secure by Design applications Integrated Offender Management (IOM) has changed and an update on how they are working since those changes were needed. In particular, information on the low-level sex offenders that they are now dealing with. These can be provided outside Corporate Performance. Connect Partnerships meeting & a paper is being prepared by Bill Scott. A request was made for the OPCC to be involved in this and receive a copy of the paper. 7th June JM is attending No Wrong Door, Together York & the Partnership Hub alongside the PCC from Northamptonshire. Briefings from the NYP perspective on how these are working are required. Problems in sending footage to Op Spartan team had been reported. RWJ to explore best practice in receiving this information from the public in various platforms (Go-Pro video, mobile phone images/videos) | 23.05.17 | Richard Anderson |  | Informaiton received and work in progress | Clsd | 27.06.17
163 | OPCC | Report back to the force performance group any early evidence of supervisor intervention post the rolling out of the training in relation to the victim investigative journey. | 23.08.16 | Thomas Thorp |  | Update 28.02.17 – After meeting with Victims Minister (Dr Philip Lee) on 27.02.17, JM requested a ‘State of the Nation Report’ on victim services in North Yorkshire. Will be circulated to Board members once completed to view before submitting to the Minister. Update 25.04.17 – TT informed the board that the report will be submitted to JM by 28.04.17. JM noted that with the approaching general election it may be sensible to have the ‘State of the Nation Report’ ready to hand to any incoming minister. Update 22.08.17 Final version on julia's desk ready to go to minster. | Clsd | 22.08.17
209 | Traffic | Written response to question posed from the public | 25.07.17 | Andy Tooke |  | Update 22.08.17 - Written reponse received and will be published online | Clsd | 22.08.17
207 | Mental Heatlh | Youth and Mental Health – Figure for York and Selby have dropped off. Find out what is impacting these figures? | 27.06.17 | Bill Scott/Jenni Newberry |  | Update 22.08.17 - Crisis team was under staffed and street triage team was been used to prop this up. Recruitment has taken place and numbers should go back up. | Clsd | 26.09.17
208 | Traffic | Speeding VS Drink Driving Accidents – what is the number of accidents on the roads? | 25.07.17 | Andy Tooke |  | Update 22.08.17 - Nationally speeding causes more accidents by 200 - 300 more. Further details will be reported once verified. | Clsd | 26.09.17
209 | Burglary | Updated report on burglary to be provided in 6 months for publication on the website | 26.09.17 | Steve Thomas |  | UPDATE 28.11.17 - Will be brought back outside of PAM | Clsd | 28.11.17
210 | Fly Tipping | Fly Tipping - to be taken through NRN and linked in with national work to find progmatic approach to this issue as it is becoming a more promanient issue | 26.09.17 | ACC Oliver |  | UPDATE 24.10.17 There is a meeting in November which someone from the NRCN is attending. We just need to find the best method of communication to ensure feedback from the meeting reaches this meeting. This is being taken forward nationally. UPDATE 28.11.17 - Been picked up nationally by NRCN. | Clsd | 28.11.17
211 | 101 | Abandonment rate for 999 calls and clarification on the routing of 999 calls. | 26.09.17 | ACC Oliver |  | UPDATE 24.10.17 This was picked up under item 7 on the agenda | Clsd | 24.10.17
212 | Kirby Misperton | Collate and respond to questions received at the meeting on item 5. Answers to those questions to be published on website | 24.10.17 | T/ACC Cain |  | UPDATE 28.11.17 reponse published on website | Clsd | 28.11.17
213 | Modern Slavery | Modern Slavery - to provide a report comparing how North Yorkshire Police performs against other forces, using relevant information the report released by HMIC on Modern Slavery. | 24.10.17 | T/ACC Cain |  | 05.01.2018 update: T/ACC Cain advised that a report will be provided for consideration at the next Public Accountability Meeting, scheduled for 23rd January 2018. 23.01.18 update: Documents will be with Julia by EOW, this will be reviewed and then the appropirate infromation publised on the website for the next meeting. | Clsd | 23.01.18
214 | 101 | Include a slide in the 101 update pack around outlayers (item 7) | 24.10.17 | DCC Winward |  | UPDATE 28.11.17 pack updated to reflect this0 | Clsd | 28.11.17
215 | Kirby Misperton | Include within the arrest figures any de-arrest information (item 5) | 24.10.17 | DCC Winward |  | UPDATE 09.11.17 Figures received and published on the website | Clsd | 28.11.17
216 |  | To engage with the control room again on induction training to share knowledge around rural crime task force, and around rural issues more generally | 24.10.17 | Insp Grainge | 27.02.18 | 23.01.18 Update: Feedback on on how this is developing and timeline for when this is likely to become part of the induction programme. 06.02.2018 Update: Dates are planned between August and October 2018 to deliver training to all five bands within the Force Control Room. | Open | 27.02.18
219 | Safeguarding | To provide, outside of the meeting, the number of offenders being managed by IOM prior to the OMU being created in 2016 and any significant aspects of how the cohort has changed over the course of this change. | 23.01.18 | Insp Harder | 27.03.18 | 05.02.2018 Update: Information in respect of the 2016 IOM cohort is provided below. There have not been any significant aspects or changes of how the cohort has changed over the course of two years. | Open | 27.02.18
220 | Safeguarding | To provide an organisational structure chart for the OMU to be published on the Police and PCC website showing the new structure and function set up | 23.01.18 | Insp Harder | 27.03.18 | 06.02.2018 Update: Please see the structure chart requested, imbedded below: | Open | 27.02.18
217 | Engagement | To engage with the various Rescue Services across North Yorkshire, re-establish senior officer links | 28.11.17 | ACC Oliver |  | 05.01.2018 update: PC Greg Davies is the new lead and links in with various Rescue Services. ACC Oliver and Supt Dave Hannan are due to attend a number of group meetings scheduled for 2018, as well as the 2018 Award Ceremony; the latter is likely to be held at NYP HQ, Alverton Court. 23.01.18 update: Application has gone into the community fund | Clsd | 23.01.17
218 | Kirby Misperton | For the Kirby Misperton Update to include de-arrest figures, backdated to September and month by month thereafter | 28.11.17 | ACC Oliver |  | 12.01.2018 update: Information around Operation Kingfisher has been submitted for circulation with meeting papers. 23.01.18 update: Information within presentation received. | Clsd | 23.01.17
222 | Minutes | Mintues from meeting 27th March, section 29 questions received from Twitter. The responses needs to be updated to better reflect the response more clearly | 24.04.18 | Evie Mortimer/Fraser Sampson | 22.05.18 | 22.05.18 Update: Notes have been updated to with a clearer response. | Clsd | 22.05.18
223 | Thematic | Crime Recording Function - What is the cost of setting up that team | 24.04.18 | Mark Proctor | 22.05.18 | 22.05.18 Update: 25.5 FTE in total. Once these posts are all in place total costs will be £636'352 | Clsd | 22.05.18
225 | Performance/Outcome Updates | Rural Taskforce - Performance slides were not included in the pack, could they be readded for next month. | 24.04.18 | ACC Oliver | 22.05.18 | 22.05.18 Update: Slides were sent separately and will be included moving forward | Clsd | 22.05.18
226 | Performance/Outcome Updates | Call Abandon Rates - The correlation changes from March, is this correct or just a mistake. | 24.04.18 | ACC Oliver | 22.05.18 | 22.05.18 Updates: Slides updated | Clsd | 22.05.18
227 | Performance/Outcome Updates | Calls for Service - The top charts are bottoms charts don't match in terms of colour coding, for ease could these be updated to reflect that | 24.04.18 | ACC Oliver | 22.05.18 | 22.05.18 Update: Slides have been updated to reflect chart colour coding | Clsd | 22.05.18
233 | Kirby Misperton | All court outcomes to be included in the updates | 22.05.18 | ACC Oliver | 26.06.18 | 26.06.18 Updates: this will be linked into the review of the operation, due to court coases still going throught he process. | Closed | 26.06.18